## Slide 1
METHODOLOGY & PROGRESS TRACKING
Kanban Board Status
Reconstructed from git log --all, branch divergence, and inspection of implementation files across all branches
DONE (6)
• Full-stack scaffold: React + FastAPI + PostgreSQL + S3 + ChromaDB
• Multi-agent grading pipeline (Parser → Grader → Auditor)
• Confidence engine (15% discrepancy threshold)
• ICC tracker vs. lecturer marks
• Human-in-the-loop review UI
• Dashboard analytics
Owner: Zoe
IN REVIEW (2)
• AI-Evaluation branch: UI polish, bulk-upload, Excel rubric parser (2 commits ahead, unmerged)
• Doc-parser branch: rubric/question splitting — latest commit flagged “(TBD)”
Owner: Zoe / Chi Shien
IN PROGRESS (3)
• LLM branch: Gemini / Claude / Nemotron role benchmarking (~$4.47 of $50 budget)
• prompt-engineering-q6-q8: Q6–Q8 tuning (uncommitted changes)
• Q22 open-ended prompt tuning
Owner: Ee Gwen / Qian Jun
BACKLOG (5)
• Authentication / access control (NFR-04)
• Performance testing: 30 submissions < 10 min (NFR-01)
• Deployment pipeline (no Docker / CI-CD found)
• Image-based grading (low priority)
• Synthesizer as a distinct 4th agent
Owner: Unassigned
gh CLI unavailable in this environment — board reconstructed directly from repository history. Branches inspected: main, AI-Evaluation, LLM, Doc-parser, PDF-parser, prompt-engineering-q6-q8, Q9-Test.

## Slide 2
METHODOLOGY & PROGRESS TRACKING
Percentage of Work Completed
Two independent calculation methods, cross-checked against the RTM and the Gantt chart
A
RTM Requirement Coverage
% = Completed Requirements ÷ Total Requirements × 100
• Completed (10): FR-01–FR-03, FR-05–FR-10, NFR-02
• In progress (4): FR-04, NFR-01, NFR-05, NFR-06
• Not started (2): NFR-03, NFR-04
Result: 10 / 16 = 62.5% (75% with half-credit for in-progress)
B
Milestone / Iteration Coverage
% = (Completed + 0.5×In-Progress) ÷ Total Milestones × 100
• Milestone 1 (Requirements/Architecture): Completed
• Milestone 2 (Core Platform): Completed
• Milestone 3 (AI Grading System): In progress
• Milestone 4 (Integration/Deployment): Not started
Result: (2 + 0.5×1) / 4 = 62.5%
Both methods converge on ~62–63% complete — consistent with the Gantt chart, which places the team partway through Iteration 3 as of 2 Sep 2026 (on schedule).

## Slide 3
METHODOLOGY & PROGRESS TRACKING
Completed vs. Remaining Milestones
Four Agile iteration milestones spanning March – October 2026
COMPLETED
• Milestone 1 — Requirements, architecture & grading model approved. Literature review, requirements elicitation, system architecture, Phase 1 LLM benchmarking (10-model ICC table) all documented.
• Milestone 2 — Core platform validated. AWS S3 + PostgreSQL + ChromaDB provisioned; React dashboard + FastAPI backend working; bulk upload, assignment creation, submission management functional.
IN PROGRESS
• Milestone 3 — Stakeholder acceptance of the AI grading system.
• ✓ Built: RAG retrieval, 3-agent grading pipeline, confidence/decision engine, ICC tracker, lecturer review + override UI, analytics dashboard.
• ↻ Open: AI-Evaluation & Doc-parser branches unmerged; LLM model-role optimisation unfinished; Q6/Q8/Q22 prompt tuning ongoing; no formal sign-off yet from Dr. Ronald.
NOT STARTED
• Milestone 4 — Integration, validation & deployment.
• Full system / UAT testing (only 1 unit test file exists repo-wide)
• Authentication / access control (NFR-04)
• Formal performance testing (10-min / 30-submission NFR)
• Deployment prep (no Docker/CI-CD config) & final stakeholder approval
Milestone framing matches the AutoGrade+ Gantt chart (Appendix 7.4) — four iteration-level milestones from the March 2026 project proposal.